***************************************************************************

USACE / NAVFAC / AFCEC / NASA          UFGS-01 32 16.05 20 (February 2015)

-----------------------------------

Preparing Activity:  NAVFAC            Superseding

UFGS-01 32 16.00 20 (July 2009)

UNIFIED FACILITIES GUIDE SPECIFICATIONS

***************************************************************************

SECTION 01 32 16.05 20

SMALL PROJECT DESIGN AND CONSTRUCTION SCHEDULES

02/15

***************************************************************************

NOTE:  This guide specification applies to Design- Build projects and covers the requirements for the preparation and use of construction schedules for small projects.  The small projects covered by this specification may be simple or complex, but would not benefit from the use of a cost-loaded NAS as required by Section 01 32 17.05 20 COST-LOADED NETWORK ANALYSIS SCHEDULES (NAS) FOR DESIGN-BUILD.  This specification includes two schedule options to choose from based on the complexity of the project. Edit this specification by choosing the desired scheduling option described below.

Confirm with the Administering FEAD/ROICC that the project schedule should be prepared under the requirements of this section.  Further, this section shall be reviewed and approved by the Administering FEAD/ROICC prior to RFP completion.

Option 1: "Non-Cost Loaded Network Analysis Schedule (NAS)" – This is the NAVFAC preferred schedule for use on most small projects and requires either Primavera P6 or Microsoft Project 2010 scheduling software to be used.  Option is provided for cost-loading Microsoft Project 2010 schedules at NAVFAC OCONUS locations where Primavera P6 support is not currently available.

Option 2: "Bar Chart Schedule" – In lieu of Option 1 for non-complex projects or projects with minimal disciplines, a simple bar chart (Non-NAS) may be specified. Project examples include: paving, painting, roof replacement, lighting, etc.

Coordination is required with Section 01 20 00.05 20 PRICE AND PAYMENT PROCEDURES FOR DESIGN-BUILD, with selection of "Schedule of Prices" for bar charts and non-cost-loaded NAS, or "Earned Value Report" for cost-loaded Microsoft Project 2010 schedules.

Adhere to UFC 1-300-02 Unified Facilities Guide Specifications (UFGS) Format Standard when editing this guide specification or preparing new project specification sections.  Edit this guide specification for project specific requirements by adding, deleting, or revising text.  For bracketed items, choose applicable items(s) or insert appropriate information.

Comments, suggestions and recommended changes for this guide specification are welcome and should be submitted as a Criteria Change Request (CCR).

***************************************************************************

# PART 1   GENERAL

## 1.1   SUBMITTALS

***************************************************************************

NOTE:  Review Submittal Description (SD) definitions in Section 01 33 00.05 20 CONSTRUCTION SUBMITTAL PROCEDURES and 01 33 10.05 20 DESIGN SUBMITTAL PROCEDURES and edit the following list to reflect only the submittals required for the project.  Keep submittals to the minimum required for quality control.

The Guide Specification technical editors have designated those items that require Government approval, due to their complexity or criticality, with a "G."  Generally, other submittal items can be reviewed by the Contractor's Quality Control System.  Only add a "G" to an item, if the submittal is sufficiently important or complex in context of the project.

An "S" following a submittal item indicates that the submittal is required for the Sustainability Notebook to fulfill federally mandated sustainable requirements in accordance with Section 01 33 29 SUSTAINABILITY REPORTING FOR DESIGN-BUILD.  Coordinate all Part 2 and Part 4 Specification Sections with 01 33 29.05 20 SUSTAINABILITY REPORTING FOR DESIGN-BUILD.

***************************************************************************

Government approval is required for submittals with a "G" designation; submittals not having a "G" designation are for Contractor Quality Control approval.  Submittals with an "S" are for inclusion in the Sustainability Notebook, in conformance with Section 01 33 29.05 20 SUSTAINABILITY REPORTING FOR DESIGN-BUILD.   Submit the following in accordance with Section 01 33 00.05 20 CONSTRUCTION SUBMITTAL PROCEDURES and 01 33 10.05 20 DESIGN SUBMITTAL PROCEDURES:

SD-01 Preconstruction Submittals

Design and Construction Schedules; G

SD-07 Certificates

Monthly Updates; G

## 1.2   ACCEPTANCE

***************************************************************************

NOTE:  Retain the applicable option in the paragraph below and edit Article "SCHEDULE FORMAT" accordingly.

***************************************************************************

Prior to the start of work, prepare and submit to the Contracting Officer for acceptance a construction schedule in the form of a [Network Analysis Schedule (NAS)][Bar Chart Schedule] in accordance with the terms in Contract Clause "FAR 52.236-15, Schedules for Construction Contracts," except as modified in this contract.

The acceptance of a Baseline Construction Schedule is a condition precedent to:

a.  The Contractor starting work on the demolition or construction stage(s) of the contract.

b.  Processing Contractor's invoice(s) for construction activities/items of work.

c.  Review of any schedule updates.

Submittal of the Baseline Construction Schedule, and subsequent schedule updates, shall be understood to be the Contractor's certification that the submitted schedule meets all of the requirements of the Contract Documents, represents the Contractor's plan on how the work shall be accomplished, and accurately reflects the work that has been accomplished and how it was sequenced (as-built logic).

## 1.3   SCHEDULE FORMAT

### [1.3.1   Network Analysis Schedule (NAS)

***************************************************************************

NOTE:  Retain this paragraph and associated subparagraphs if Option 1 (described in the Initial Editing Notes) is applicable and a NAS is required for the project.

***************************************************************************

The Contractor shall use the critical path method (CPM) to schedule and control project activities. Project schedules shall be prepared and maintained using [Primavera P6][or][Microsoft Project 2010]. Importing data into the scheduling program using data conversion techniques or third party software will be cause for rejection of the submitted schedule. The schedule shall be built as follows:

The Project Schedule shall show design periods, submittals, Government review periods, material/equipment delivery, utility outages, all on-site construction, inspection, testing, and closeout activities. Government and Contractor on-site work activities shall be driven by calendars that reflect Saturdays, Sundays and all Federal Holidays as non-work days.

With the exception of the Contract Award and End Contract milestone activities, no activities shall be open-ended; each activity shall have predecessor and successor ties.  No activity shall have open start or open finish (dangling) logic.  Redundant logic ties shall be minimized.  Once an activity exists on the schedule it may not be deleted or renamed to change the scope of the activity and shall not be removed from the schedule logic without approval from the Contracting Officer.  While an activity cannot be deleted, where said activity is no longer applicable to the schedule but shall remain within the logic stream for historical record, it can be changed to a milestone.  Any such change shall be documented in the milestone's "Notebook", including a date and explanation for the change.  The ID number for a deleted activity shall not be re-used for another activity.

Each activity shall be assigned its appropriate Responsibility Code indicating responsibility to accomplish the work indicated by the activity, Phase Code and Work Location Code.

Date/time constraint(s) and/or lags, other than those required by the contract, shall not be allowed unless accepted by the Contracting Officer. The Contractor shall include as the last activity in the contract schedule, a milestone activity named "Contract Completion Date".

#### [1.3.1.1   Primavera P6 Settings and Parameters

***************************************************************************

NOTE:  Retain this Paragraph for NAS schedules using Primavera P6.  Delete for NAS schedules using Microsoft Project 2010.

***************************************************************************

Primavera P6 settings and parameters which shall be used in preparing the Baseline Schedule are as follows.  Deviation from these settings and parameters, without prior consent of the Contracting Officer, will be cause for rejection of schedule submission.

a.  General: Calendars and Activity Codes are defined or established at the "Project" level, not the "Global" level.

b.  Admin Drop-Down Menu, Admin Preferences, Time Periods Tab:

(1) Time periods for P6 shall be set to 8.0 Hours/Day, 40.0 Hours/Week, 172.0 Hours/Month and 2000.0 Hours/Year.

(2) Use assigned calendar to specify the number of work hours for each time period: Shall be checked.

c.  Project Level, Dates Tab:

(1) Set "Must Finish By" date to "Contract Completion Date".

d.  Project Level, Defaults Tab:

(1) Duration Type: Set to "Fixed Duration & Units".

(2) Percent Complete Type: Set to "Physical".

(3) Activity Type: Set to "Task Dependent".

(4) Calendar: Set to "Standard 5 Day Workweek".  Calendar shall reflect Saturday, Sunday and all Federal holidays as non-work days.  Alternative calendars may be used with Contracting Officer approval.

e.  Project Level, Calculations Tab:

(1) Activity percent complete based on activity steps: Shall be Checked.

(2) Reset Remaining Duration and Units to Original: Shall be Checked.

(3) Subtract Actual from At Completion: Shall be Checked.

(4) Recalculate Actual units and Cost when duration % complete changes: Shall be Checked.

(5) Link Actual to Date and Actual This Period Units and Cost: Shall be Checked.

f.  Project Level, Settings Tab:

(1) Define Critical Activities: Check "Total Float is less than or equal to" and add "0d".

g.  No on-site construction activity shall have durations in excess of 20 working days.

#### ][1.3.1.2   Microsoft Project 2010 Settings and Parameters

***************************************************************************

NOTE:  Retain this Paragraph for NAS schedules using Microsoft Project 2010.  Delete for NAS schedules using Primavera P6.

This paragraph is expected to be expanded as additional settings requirements are established for Microsoft Project 2010 applications.

***************************************************************************

The Network shall have a minimum of 30 construction activities.  No on-site construction activity shall have durations in excess of 20 working days.

##### [1.3.1.2.1   Cost Loading Microsoft Project 2010 Schedules

***************************************************************************

NOTE:  Retain this Paragraph only when cost loading a Microsoft Project 2010 schedule.

***************************************************************************

Material, labor and equipment costs will be assigned to their respective Construction Activities.  Material and equipment costs for which payment will be requested in advance of installation will be assigned to their respective procurement activity (i.e. the material/equipment on-site activity).  Evenly disperse overhead and profit to each activity over the duration of the project.  Cost loading shall total to 100 percent of the value of the contract.

a.  Submit an Earned Value Report with each schedule update showing activity budget, cost percent complete, earned amount and cost to complete as directed by the Contracting Officer.

b.  With each schedule submission, provide a Schedule Variance control (SVC) diagram showing:

(1) Cash Flow S-Curves indicating planned project cost based on projected early and late activity finish dates.

(2) Earned Value to-date.  Revise Cash Flow S-Curves when the contract is modified, or as directed by the Contracting Officer.

### ]]][1.3.2   Bar Chart Schedule

***************************************************************************

NOTE:  Retain this paragraph if Option 2 (described in the Initial Editing Notes) is applicable and a Bar Chart is required for the project.

***************************************************************************

The Bar Chart shall show submittals, Government review periods, material/equipment delivery, utility outages, on-site construction, inspection, testing, and closeout activities.  The Bar Chart shall be time scaled and generated using an electronic spreadsheet program.

### ]1.3.3   Schedule Submittals and Procedures

Submit [Network Analysis Schedules (NAS)][Bar Chart Schedules] and updates in hard copy and on electronic media that is acceptable to the Contracting Officer.  Submit an electronic back-up of the project schedule in an import format compatible with the Government's scheduling program.

## 1.4   SCHEDULE MONTHLY UPDATES

Update the Design and Construction Schedules at monthly intervals or when the schedule has been revised. The updated schedule shall be kept current, reflecting actual activity progress and plan for completing the remaining work. Submit copies of purchase orders and confirmation of delivery dates as directed.

a.  Narrative Report: Provide with schedule updates.  Identify and justify;

(1) Progress made in each area of the project

(2) Critical Path

(3) Date/time constraint(s), other than those required by the contract

(4) Changes in the following; added or deleted activities, original and remaining durations for activities that have not started, logic, milestones, planned sequence of operations, and critical path

(5) Status of Contract Completion Date and interim milestones;

(6) Current and anticipated delays (describe cause of delay and corrective actions(s) and mitigation measures to minimize);

(7) Description of current and future schedule problem areas.

Each entry in the narrative report will cite the respective Activity ID and Activity Description, the date and reason for the change, and description of the change.

## [1.5   CONTRACT MODIFICATION

***************************************************************************

NOTE:  Retain this Article for projects with NAS schedules.

***************************************************************************

Submit a Time Impact Analysis (TIA) with each cost and time proposal for a proposed change.  TIA shall illustrate the influence of each change or delay on the Contract Completion Date or milestones.  No time extensions will be granted nor delay damages paid unless a delay occurs which consumes all available Project Float, and extends the Projected Finish beyond the Contract Completion Date.

a.  Each TIA shall be in both narrative and schedule form.  The narrative shall define the scope and conditions of the change; provide start and finish dates of impact, successor and predecessor activity to impact period, responsible party, describe how it originated, and how it impacts the schedule.   The schedule submission shall consist of three native files:

(1) Fragnet used to define the scope of the changed condition.

(2) Most recent accepted schedule update as of the time of the proposal or claim submission that has been updated to show all activity progress as of the time of the impact start date.

(3) The impacted schedule that has the fragnet inserted in the updated schedule and the schedule "run" so that the new completion date is determined.

b.  If the impact has not occurred within 30 calendar days, TIA procedure shall be reduced to the most basic level possible to still reflect a reasonable assessment of the result of a delay, representing actual conditions as they occurred.

c.  All TIAs shall include any mitigation, and shall determine the apportionment of the overall delay assignable to each individual delay.  The associated narrative shall clearly describe the findings in a chronological listing beginning with the earliest delay event.

(1) Identify types of delays as follows:

(a) Excusable Delay: Force-Majeure (e.g. weather) - Contractor may receive time extension, but time will not be compensable.

(b)  Inexcusable Delay: Contractor Responsibility - Contractor shall not receive time extension.

(c)  Compensable Delay: Government Responsibility - Contractor may receive compensable time extension.

(2) If a combination of delay types occurs, it is considered Concurrent Delay, which is defined in the following combinations:

(a) Excusable Delay and Compensable Delay results in Excusable Delay

(b) Excusable Delay and Inexcusable Delay results in Inexcusable Delay

(c) Compensable Delay and Inexcusable Delay results in Excusable Delay

d.  Submit Data disks containing the narrative and native schedule files.

e.  Unless the Contracting Officer requests otherwise, only conformed contract modifications shall be added into the Project NAS.

## ]1.6   THREE-WEEK LOOK AHEAD SCHEDULE

The Contractor shall prepare and issue a 3-Week Look Ahead schedule to provide a more detailed day-to-day plan of upcoming work identified on the Design and Construction Schedules.  The work plans shall be keyed to activity numbers when a NAS is required and updated each week to show the planned work for the current and following two-week period.  Additionally, include upcoming outages, closures, preparatory meetings, and initial meetings.  Identify critical path activities on the Three-Week Look Ahead Schedule.  The detail work plans are to be bar chart type schedules, maintained separately from the Design and Construction Schedules on an electronic spreadsheet program and printed on 8-1/2 by 11 sheets as directed by the Contracting Officer.  Activities shall not exceed 5 working days in duration and have sufficient level of detail to assign crews, tools and equipment required to complete the work.  Three hard copies and one electronic file of the 3-Week Look Ahead Schedule shall be delivered to the Contracting Officer no later than 8 a.m. each Monday and reviewed during the weekly CQC Coordination and/or Production Meeting.

## 1.7   CORRESPONDENCE AND TEST REPORTS

All correspondence (e.g., letters, Requests for Information (RFIs), e-mails, meeting minute items, Production and QC Daily Reports, material delivery tickets, photographs, etc.) shall reference Schedule Activities that are being addressed.  All test reports (e.g., concrete, soil compaction, weld, pressure, etc.) shall reference Schedule Activities that are being addressed.

## 1.8   ADDITIONAL SCHEDULING REQUIREMENTS

Any references to additional scheduling requirements, including systems to be inspected, tested and commissioned, that are located throughout the remainder of the Contract Documents, shall be subject to all requirement of this section.

# PART 2   PRODUCTS

Not used.

# PART 3   EXECUTION

Not used.

-- End of Section --