SECTION 01702 - PROJECT CLOSEOUT - LEAD BASED PAINT

PART

1 - GENERAL

1.1	RELATED DOCUMENTS

A.	Drawings and general provisions of the Contract, including General and Supplementary Conditions and other Division-1 Specification Sections, apply to this Section.

1.2	SUMMARY

A.	This Section specifies administrative and procedural requirements for project closeout, including but not limited to:

1.	Inspection procedures.

2.	Project record document submittal.

3.	Submittal of warranties.

4.	Final cleaning.

B.	Closeout requirements for specific construction activities are included in the appropriate Sections in Divisions-2 through -16.

1.3	SUBSTANTIAL COMPLETION

A.	Preliminary Procedures:  Before requesting inspection for certification of Substantial Completion, complete the following.  List exceptions in the request.

1.	In the Application for Payment that coincides with, or first follows, the date Substantial Completion is claimed, show 100 percent completion for the portion of the Work claimed as substantially complete.  Include supporting documentation for completion as indicated in these Contract Documents and a statement showing an accounting of changes to the Contract Sum.

a.	If 100 percent completion cannot be shown, include a list of incomplete items, the value of incomplete construction, and reasons the Work is not complete.

2.	Advise Owner of pending insurance change-over requirements.

3.	Submit specific warranties, workmanship bonds, maintenance agreements, final certifications and similar documents.

4.	Obtain and submit releases enabling the Owner unrestricted use of the Work and access to services and utilities; include occupancy permits, operating certificates and similar releases.

5.	Submit record drawings, maintenance manuals, final project photographs, damage or settlement survey, property survey, and similar final record information.

6.	Deliver tools, spare parts, extra stock, and similar items.

7.	Make final change-over of permanent locks and transmit keys to the Owner.  Advise the Owner's personnel of change-over in security provisions.

8.	Complete start-up testing of systems, and instruction of the Owner's operating and maintenance personnel.  Discontinue or change over and remove temporary facilities from the site, along with construction tools, mock-ups, and similar elements.

9.	Complete final clean up requirements, including touch-up painting.  Touch-up and otherwise repair and restore marred exposed finishes.

B.	Inspection Procedures:  On receipt of a request for inspection, the Designer will either proceed with inspection or advise the Contractor of unfilled requirements.  The Designer will prepare the Certificate of Substantial Completion following inspection, or advise the Contractor of construction that must be completed or corrected before the certificate will be issued.

1.	The Designer will repeat inspection when requested and assured that the Work has been substantially completed.

2.	Results of the completed inspection will form the basis of requirements for final acceptance.

1.4	FINAL ACCEPTANCE

A.	Preliminary Procedures:  Before requesting final inspection for certification of final acceptance and final payment, complete the following.  List exceptions in the request.

1.	Submit the final payment request with releases and supporting documentation not previously submitted and accepted.  Include certificates of insurance for products and completed operations where required.

2.	Submit an updated final statement, accounting for final additional changes to the Contract Sum.

3.	Submit a certified copy of the Designer final inspection list of items to be completed or corrected, stating that each item has been completed or otherwise resolved for acceptance, and the list has been endorsed and dated by the Designer.

4.	Submit final meter readings for utilities, a measured record of stored fuel, and similar data as of the date of Substantial Completion, or when the Owner took possession of and responsibility for corresponding elements of the Work.

5.	Submit consent of surety to final payment.

6.	Submit a final liquidated damages settlement statement.

7.	Submit evidence of final, continuing insurance coverage complying with insurance requirements.

B.	Reinspection Procedure:  The Designer will reinspect the Work upon receipt of notice that the Work, including inspection list items from earlier inspections, has been completed, except items whose completion has been delayed because of circumstances acceptable to the Designer.

1.	Upon completion of reinspection, the Designer will prepare a certificate of final acceptance, or advise the Contractor of Work that is incomplete or of obligations that have not been fulfilled but are required for final acceptance.

2.	If necessary, reinspection will be repeated.

1.5	RECORD DOCUMENT SUBMITTALS

A.	General:  Do not use record documents for construction purposes; protect from deterioration and loss in a secure, fire-resistive location; provide access to record documents for the Designer's reference during normal working hours.

B.	Record Drawings:  Maintain a clean, undamaged set of blue or black line white-prints of Contract Drawings and Shop Drawings.  Mark the set to show the actual installation where the installation varies substantially from the Work as originally shown.  Mark whichever drawing is most capable of showing conditions fully and accurately; where Shop Drawings are used, record a cross-reference at the corresponding location on the Contract Drawings.  Give particular attention to concealed elements that would be difficult to measure and record at a later date.

1.	Mark record sets with red erasable pencil; use other colors to distinguish between variations in separate categories of the Work.

2.	Mark new information that is important to the Owner, but was not shown on Contract Drawings or Shop Drawings.

3.	Note related Change Order numbers where applicable.

4.	Organize record drawing sheets into manageable sets, bind with durable paper cover sheets, and print suitable titles, dates and other identification on the cover of each set.

C.	Record Specifications:  Maintain one complete copy of the Project Manual, including addenda, and one copy of other written construction documents such as Change Orders and modifications issued in printed form during construction.  Mark these documents to show substantial variations in actual Work performed in comparison with the text of the Specifications and modifications. Give particular attention to substitutions, selection of options and similar information on elements that are concealed or cannot otherwise be readily discerned later by direct observation.  Note related record drawing information and Product Data.

5.	Upon completion of the Work, submit record Specifications to the Designer for the Owner's records.

C.	Record Product Data:  Maintain one copy of each Product Data submittal.  Mark these documents to show significant variations in actual Work performed in comparison with information submitted.  Include variations in products delivered to the site, and from the manufacturer's installation instructions and recommendations.  Give particular attention to concealed products and portions of the Work which cannot otherwise be readily discerned later by direct observation.  Note related Change Orders and mark-up of record drawings and Specifications.

1.	Upon completion of mark-up, submit complete set of record Product Data to the Designer for the Owner's records.

D.	Record Sample Submitted:  Immediately prior to the date or dates of Substantial Completion, the Contractor will meet at the site with the Designer and the Owner's personnel to determine which of the submitted Samples that have been maintained during progress of the Work are to be transmitted to the Owner for record purposes.  Comply with delivery to the Owner's Sample storage area.

E.	Miscellaneous Record Submittals:  Refer to other Specification Sections for requirements of miscellaneous record-keeping and submittals in connection with actual performance of the Work.  Immediately prior to the date or dates of Substantial Completion, complete miscellaneous records and place in good order, properly identified and bound or filed, ready for continued use and reference.  Submit to the Designer for the Owner's records.

PART 2 - PRODUCTS (Not Applicable)

PART 3 - EXECUTION

3.1	FINAL HOUSEKEEPING

A.	General:  General cleaning during construction is required by the General Conditions and included in Section "Temporary Facilities".

B.	Cleaning:  Employ experienced workers or professional cleaners for final cleaning.  Clean each surface or unit to the condition expected in a normal, commercial building cleaning and maintenance program.  Comply with manufacturer's instructions.

1.	Complete the following cleaning operations before requesting inspection for Certification of Substantial Completion.

a.	Remove labels that are not permanent labels.

b.	Clean transparent materials, including mirrors and glass in doors and windows.  Remove glazing compound and other substances that are noticeable vision-obscuring materials.  Replace chipped or broken glass and other damaged transparent materials.

c.	Clean exposed exterior and interior hard-surfaced finishes to a dust-free condition, free of stains, films and similar foreign substances.  Restore reflective surfaces to their original reflective condition.  Leave concrete floors broom clean.  Vacuum carpeted surfaces.

d.	Wipe surfaces of mechanical and electrical equipment.  Remove excess lubrication and other substances.  Clean plumbing fixtures to a sanitary condition.  Clean light fixtures and lamps.

e.	Clean the site, including landscape development areas, of rubbish, litter and other foreign substances.  Sweep paved areas broom clean; remove stains, spills and other foreign deposits.  Rake grounds that are neither paved nor planted, to a smooth even-textured surface.

C.	Removal of Protection:  Remove temporary protection and facilities installed for protection of the Work during construction.

D.	Compliance:  Comply with regulations of authorities having jurisdiction and safety standards for cleaning.  Do not burn waste materials.  Do not bury debris or excess materials on the Owner's property.  Do not discharge volatile, harmful or dangerous materials into drainage systems.  Remove waste materials from the site and dispose of in a lawful manner.

1.	Where extra materials of value remaining after completion of associated Work have become the Owner's property, arrange for disposition of these materials as directed.

END OF SECTION 01702